## Section 151. — MOBILIZATION

09/17/18–FP14

WFL Specification 09/17/18 1510010

Include the following on Alaska projects that require barging of equipment and materials to the project site.

Coordinate with the COE to determine if this SCR should be used.

Payment

### 151.03

Delete paragraphs (c) and (d) and substitute the following:

**(c)** When 10 percent of the original contract amount is earned from pay items (not including mobilization), the lesser of the following will be paid:

**(1)** 100 percent of the mobilization pay item, including the paid invoice cost for barging equipment and materials to the site; or,

**(2)** 10 percent of the original contract amount plus the paid invoice cost for barging equipment and materials to the site.

**(d)** Any portion of the mobilization pay item exceeding the amount paid under Subsection 151.03(c) will be paid after final acceptance.

WFL Specification 09/17/18 1510020

Include the following with MATOC projects.

Payment

### 151.03

Delete the text of this Subsection and substitute the following:

The accepted quantities will be paid at the task order price per unit of measurement for the Section 151 pay items listed in the bid schedule. Payment will be full compensation for the work prescribed in this Section. See Subsection 109.05.

Progress payments for mobilization by the lump sum will be paid as follows:

**(a)** Bond premiums will be reimbursed according to FAR Clause 52.232-5 Payments Under Fixed-Price Construction Contracts, after receipt of the evidence of payment.

**(b)** When 5 percent of the original task order amount is earned from pay items (not including mobilization), 50 percent of the mobilization item, or 5 percent of the original task order amount, whichever is less, will be paid.

**(c)** When 10 percent of the original task order amount is earned from pay items (not including mobilization), 100 percent of the mobilization item, or 10 percent of the original task order amount, whichever is less, will be paid.

**(d)** Any portion of the mobilization pay item exceeding 10 percent of the original task order amount will be paid after final acceptance.